AI Governance Compliance Tracker

Project Proposal and Plan

Project: 2026-S2R-04

Sponsor organisation: Sri Ramakrishna Engineering College

Sponsor name: P.Monisha

Project team: Avnish Suresh (U3258126), Ashvin Kumar (U3280817), Noorpreet Badwal (U3215790) and Jordon Hayden (U3207566)

Primary users: Faculty within an educational institution

Sponsor meeting cadence: Fortnightly

Status: Current proposal based on confirmed sponsor direction and project requirements; selected items remain subject to sponsor clarification.

# Executive Summary

This project proposes a web-based AI Governance Compliance Tracker for an educational institution. The system will support faculty use of AI across education, administration and research by providing a structured mechanism to register AI tools and use cases, assess governance maturity and risk, track compliance actions and monitor institution-wide governance status.

The supplied capstone requirements establish a broader functional baseline including authentication and role-based access, a governance self-assessment mapped to recognised frameworks, an AI registry, rules-based risk scoring, policy document management, action tracking, reminders, reporting, an administrator dashboard and Shadow AI self-reporting. The proposal retains these requirements while adapting their original SME framing to the sponsor-confirmed educational-institution context. The intended outcome is a credible, well-tested prototype that can form a foundation for future development, together with an accompanying research paper.

# 1. Requirements Basis and Current Project Direction

| Source | Confirmed / Required Direction |
| --- | --- |
| Sponsor meeting | Educational institution; faculty users; AI used in education, administration and research; focus on governance, risk, compliance and security; practical prototype; research paper; fortnightly meetings. |
| Capstone requirements document | Web application; authentication/RBAC; framework-mapped self-assessment; AI registry; rules-based risk scoring; policy repository; action tracking; reminders; reporting; dashboard; Shadow AI self-reporting; secure/privacy-conscious design; testing and handover documentation. |
| Still requiring sponsor confirmation | Detailed institutional problem statement; exact institutional policies; precise user roles/approval workflow; preferred framework weighting; infrastructure/deployment expectations; research-paper format and evaluation expectations. |

# 2. Problem Definition, Context, Scope and Objectives

## 2.1 Context and Preliminary Problem

Educational institutions are increasingly adopting AI in teaching and learning, administrative work and research. This creates opportunities for productivity and innovation, but also introduces risks relating to privacy, security, accountability, transparency, research integrity, appropriate use and institutional compliance. AI may also be adopted informally by individual users before an institution has visibility of the tool, its purpose or the data it processes.

The original capstone requirements describe this visibility problem as 'Shadow AI' and propose a practical governance workflow of assessing AI governance maturity, registering and risk-classifying AI tools, tracking policy/compliance actions and producing management or audit-oriented reports. For this project, that workflow is adapted to an educational institution and faculty users rather than SMEs.

## 2.2 Proposed Problem Statement

The educational institution requires a practical mechanism to gain visibility over AI tools and use cases used by faculty across education, administration and research; assess those uses against recognised governance principles and institutional requirements; identify and track governance actions; and provide evidence of the institution's AI governance and compliance activity through a central dashboard and reporting workflow.

## 2.3 Objectives

- Create a central register of AI tools/systems/use cases used by faculty.

- Classify AI use across education, administration and research.

- Translate recognised AI governance frameworks into a structured self-assessment suitable for faculty users.

- Apply transparent rules-based risk classification to registered AI use cases.

- Track governance/compliance actions, ownership, due dates and completion status.

- Provide role-appropriate dashboards and an institution-wide governance overview.

- Support policy/evidence management, reminders and Shadow AI self-reporting.

- Generate PDF/CSV compliance summaries suitable for management or review.

- Use secure, privacy-conscious and maintainable software engineering practices.

- Deliver a practical prototype, handover documentation and accompanying research paper.

## 2.4 Scope

| In Scope | Out of Scope |
| --- | --- |
| Responsive web application for desktop/tablet | Production deployment, commercial hosting or ongoing support |
| Authentication and role-based access | Live enterprise SSO/identity integration |
| Framework-mapped governance self-assessment | Formal legal/regulatory certification or compliance sign-off |
| AI tool/system/use-case registry | Automated network/device-level Shadow AI detection |
| Rules-based Low/Medium/High risk classification | Machine-learning-based compliance decisions |
| Policy document repository | Deepfake detection or AI-content forensics |
| Compliance action tracker and reminders | Large-scale performance/load testing |
| Role-based dashboards and traffic-light overview | Multi-jurisdictional regulatory mapping unless requested |
| PDF/CSV reporting/export | Live integrations with production SaaS/cloud admin APIs |
| Shadow AI self-reporting form | Real sensitive student/staff/research data during development |
| Fictional/de-identified demo data |  |
| Architecture, user guide and handover documentation |  |

## 2.5 Stretch Goals

- AI-assisted analysis of uploaded policy documents to identify potential gaps against a reference framework.

- Common AI-tool lookup to pre-populate basic tool/risk information.

- Multi-organisation or multi-department tenant support beyond the minimum prototype.

- Additional analytics or external integrations requested by the sponsor.

# 3. Background and Literature Review Direction

The research component will examine how recognised AI governance frameworks can be operationalised through a usable software workflow in higher education. The capstone requirements identify the NIST AI Risk Management Framework, Australia's AI Ethics Principles, ISO/IEC 42001 and Australian privacy guidance as key references. These sources converge on themes including governance accountability, risk identification and management, privacy, transparency, human oversight and ongoing monitoring.

The literature review will extend the original SME-focused literature direction into the higher-education context. The formal literature review should examine AI governance in teaching, administration and research, including privacy and security, academic/research integrity, fairness, human oversight, institutional policy, and the governance risks created when AI tools are adopted without formal visibility or approval.

The project's research contribution is not to create a new legal compliance standard. It is to investigate and demonstrate how abstract governance requirements can be translated into a practical assessment-register-track-report workflow for faculty and institutional governance.

# 4. Requirements Analysis

## 4.1 Functional Requirements

| ID | Requirement | Priority | Basis |
| --- | --- | --- | --- |
| FR-01 | User registration and secure authentication. | High | Capstone requirement |
| FR-02 | Role-based login/authorisation supporting Administrator, Compliance/Governance Officer and Faculty/Staff User roles, subject to sponsor confirmation of role names. | High | Capstone requirement adapted to faculty context |
| FR-03 | Structured AI governance self-assessment mapped to recognised reference frameworks. | High | Capstone requirement |
| FR-04 | AI registry to record tool/system/use case, purpose, education/admin/research category, data sensitivity and approval status. | High | Capstone + sponsor context |
| FR-05 | Rules-based risk-scoring engine classifying registered AI use cases, e.g. Low/Medium/High. | High | Capstone requirement |
| FR-06 | Risk result provides transparent/explainable reasons based on assessment responses. | High | Derived quality requirement |
| FR-07 | Policy document repository allows policies/evidence to be uploaded and linked to checklist items. | High | Capstone requirement |
| FR-08 | Compliance action tracker supports owner, due date and Not Started/In Progress/Complete status. | High | Capstone requirement |
| FR-09 | Automated reminders for upcoming/overdue actions and policy reviews. | High | Capstone requirement |
| FR-10 | Administrator/governance dashboard summarises institution-wide compliance posture using clear status indicators. | High | Capstone + sponsor direction |
| FR-11 | Role-based dashboards expose appropriate information/functions to different user types. | High | Capstone requirement |
| FR-12 | Reporting module exports compliance summaries in PDF/CSV format. | High | Capstone requirement |
| FR-13 | Shadow AI self-reporting form allows faculty/staff to disclose AI tools not formally registered. | High | Capstone requirement |
| FR-14 | Users can view/filter AI uses by Education, Administration and Research. | Medium | Sponsor-context requirement |
| FR-15 | System maintains sufficient status/history information to demonstrate tracking and monitoring over time. | Medium | Derived from sponsor purpose |

## 4.2 Non-Functional Requirements

| ID | Requirement |
| --- | --- |
| NFR-01 Security | Encrypted transmission (HTTPS/TLS), secure password handling and role-based access control. |
| NFR-02 Privacy | Align design with relevant Australian privacy principles/guidance and use fictional/de-identified data during development/testing. |
| NFR-03 Usability | Plain-language interface with minimal governance/technical jargon, adapted for faculty users. |
| NFR-04 Reliability | Core assessment/tracking functions tested through unit/integration and functional testing. |
| NFR-05 Scalability | Architecture should permit separation of organisations/departments/tenants even if demonstrated only at prototype scale. |
| NFR-06 Maintainability | Clean, documented, version-controlled codebase with architecture and handover guidance. |
| NFR-07 Performance | Dashboard and reports should respond acceptably with small-to-medium demonstration datasets. |
| NFR-08 Accessibility | Responsive, readable and keyboard-accessible interface with appropriate contrast and semantic structure. |
| NFR-09 Explainability | Risk classifications and governance status must be traceable to responses/rules/framework mapping. |

# 5. Proposed Solution and Architecture

The proposed product is a three-tier web application: a single-page frontend for faculty assessments, registry, dashboards and reporting; a backend API responsible for authentication, authorisation, business rules, reminders and risk scoring; and a relational database storing users, AI registry records, assessments, governance actions and related metadata. Policy documents may be stored through a simple file-storage layer appropriate to the prototype.

## 5.1 Core Workflow

Faculty login → register AI tool/use case → classify as Education/Administration/Research → complete governance assessment → rules engine calculates risk/status → governance actions are created/tracked → dashboard monitors posture → report/export produced.

## 5.2 Proposed Technology Direction

A modern web stack consistent with the capstone requirements is recommended: React/Vue/Angular frontend; Node.js or Python-based backend; relational database such as PostgreSQL/MySQL; REST APIs; Git/GitHub version control; and standard libraries/services for dashboards, document handling and report generation. The final stack should be confirmed based on team capability and sponsor infrastructure.

# 6. Brief Justification of the Chosen Option / Method

A web-based prototype using a standard three-tier architecture is preferred because it directly supports the required assessment, registry, tracking, dashboard and reporting workflow while remaining achievable within a capstone semester. The supplied project requirements propose a frontend single-page application, backend API and relational database, with transparent rules-based risk scoring rather than machine-learning-based compliance decisions.

An Agile delivery approach is appropriate because several institutional requirements remain subject to sponsor clarification and the sponsor has agreed to fortnightly engagement. Iterative development allows the team to demonstrate working increments, capture feedback and adjust lower-priority scope while protecting the core prototype.

# 7. Detailed Project Plan and Schedule

The schedule includes resources, milestones, individual effort estimates and a Work Breakdown Structure as required by the assessment. Hours are planning estimates and may be re-baselined after remaining sponsor requirements are confirmed.

## 7.1 Resource Requirements

| Type | Resource | Purpose |
| --- | --- | --- |
| People | Jordon, Avnish, Ashvin, Noorpreet | Research, requirements, design, development, testing, documentation and presentation. |
| Sponsor | Monisha – Sri Ramakrishna Engineering College | Requirements clarification, fortnightly reviews and feedback. |
| Academic support | Shaun / course convenors | Mentoring, project guidance and escalation. |
| Development | React/Vue/Angular; Node.js/Express or Python/Flask; relational DB | Proposed implementation stack; final choice subject to team agreement. |
| Version control | Git/GitHub | Source control, branching, review and traceability. |
| Project management | Ticket register + shared workspace | Task allocation, defects, status and evidence. |
| Collaboration | Google Drive, WhatsApp, email, video meetings | Documents, minutes and sponsor coordination. |
| Infrastructure | Local dev environment; optional hosted demo | Prototype development and demonstration. |

## 7.2 Milestones and Deadlines

| Milestone | Target | Output |
| --- | --- | --- |
| M1 Proposal baseline | Week 4 | Proposal/plan, requirements, WBS, schedule, risks and stakeholders. |
| M2 Requirements/design baseline | End W5 | Prioritised requirements, journeys, wireframes, data model and scoring design. |
| M3 Core prototype | End W7 | Authentication/RBAC, AI registry, classification, assessment and risk scoring. |
| M4 Governance features | End W9 | Policy repository, actions, reminders and dashboard. |
| M5 Sponsor review | W10 | Working demonstration, feedback and change list. |
| M6 Reporting/usability | End W11 | PDF/CSV reporting, Shadow AI form and accessibility/UI refinement. |
| M7 Testing complete | End W12 | Functional/UAT evidence, defects fixed, security/privacy review. |
| M8 Final delivery | W13 | Final demo, documentation, handover and research output. |

## 7.3 Gantt Chart

| Activity | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proposal & requirements | ● | ● |  |  |  |  |  |  |  |  |
| Literature/background | ● | ● | ● |  |  |  |  |  |  |  |
| Framework mapping | ● | ● | ● |  |  |  |  |  |  |  |
| UX/wireframes | ● | ● |  |  |  |  |  |  |  |  |
| Architecture/database/risk design | ● | ● |  |  |  |  |  |  |  |  |
| Sprint 1 – auth & registry |  | ● | ● | ● |  |  |  |  |  |  |
| Sprint 1 – assessment/risk |  |  | ● | ● |  |  |  |  |  |  |
| Sprint 2 – policy/actions/reminders |  |  |  |  | ● | ● |  |  |  |  |
| Sprint 2 – dashboard |  |  |  |  | ● | ● |  |  |  |  |
| Sponsor review |  |  |  |  |  |  | ● |  |  |  |
| Sprint 3 – reporting/Shadow AI |  |  |  |  |  |  | ● | ● |  |  |
| Accessibility/UI refinement |  |  |  |  |  |  |  | ● |  |  |
| Testing/UAT/defects |  |  |  |  |  |  |  | ● | ● |  |
| Research paper/documentation |  |  |  |  |  | ● | ● | ● | ● | ● |
| Final demo/handover |  |  |  |  |  |  |  |  |  | ● |

## 7.4 Work Breakdown Structure (WBS), Effort and Allocation

| WBS | Activity | Owner | Hours | Timing |
| --- | --- | --- | --- | --- |
| 1.1 | Sponsor requirements/scope | Jordon | 8 | W4–5 |
| 1.2 | Proposal/planning integration | Avnish | 8 | W4 |
| 1.3 | Background/literature research | Ashvin | 10 | W4–6 |
| 1.4 | Framework mapping research | Noorpreet | 10 | W4–6 |
| 2.1 | User journeys | Jordon | 6 | W4–5 |
| 2.2 | Wireframes/UI design | Noorpreet | 8 | W4–5 |
| 2.3 | Database model | Ashvin | 8 | W4–5 |
| 2.4 | Architecture/API design | Avnish | 8 | W4–5 |
| 2.5 | Risk-scoring design | Jordon + Ashvin | 10 total | W4–5 |
| 3.1 | Repo/dev setup | Avnish | 5 | W5 |
| 3.2 | Authentication/RBAC | Avnish | 14 | W5–7 |
| 3.3 | AI registry | Jordon | 16 | W5–7 |
| 3.4 | Edu/Admin/Research classification | Jordon | 6 | W5–7 |
| 3.5 | Governance questionnaire | Noorpreet | 16 | W6–7 |
| 3.6 | Risk scoring/explanation | Ashvin | 16 | W6–7 |
| 4.1 | Policy/evidence repository | Noorpreet | 12 | W8–9 |
| 4.2 | Action tracker | Jordon | 12 | W8–9 |
| 4.3 | Reminders | Avnish | 10 | W8–9 |
| 4.4 | Dashboard | Ashvin | 14 | W8–9 |
| 5.1 | Sponsor demo | All | 8 total | W10 |
| 5.2 | Feedback/backlog refinement | Jordon | 5 | W10 |
| 6.1 | PDF/CSV export | Avnish | 10 | W10–11 |
| 6.2 | Shadow AI form | Noorpreet | 8 | W10–11 |
| 6.3 | Dashboard/UI refinement | Ashvin | 8 | W10–11 |
| 6.4 | Accessibility/usability | Jordon | 8 | W11 |
| 7.1 | Unit/integration tests | Avnish + Ashvin | 16 total | W11–12 |
| 7.2 | Functional/UAT | Jordon + Noorpreet | 16 total | W11–12 |
| 7.3 | Security/privacy review | Ashvin | 6 | W12 |
| 7.4 | Defects/regression | All | 20 total | W12 |
| 8.1 | Research methodology/evaluation | Noorpreet | 8 | W9–11 |
| 8.2 | Research paper | All | 28 total | W9–13 |
| 8.3 | README/architecture/user guide | Avnish + Jordon | 14 total | W12–13 |
| 8.4 | Final demo/handover | All | 16 total | W13 |

## 7.5 Individual Effort Summary

| Member | Indicative Hours | Primary Areas |
| --- | --- | --- |
| Jordon | ~91 | Sponsor/requirements, registry, actions, usability, testing, documentation/research. |
| Avnish | ~83 | Planning, architecture, DevOps, auth/RBAC, reminders, reporting, testing/documentation. |
| Ashvin | ~82 | Research/data design, risk model, dashboard, testing/security and research. |
| Noorpreet | ~78 | Framework research, UX, assessment, policy repository, Shadow AI, UAT/research. |

# 8. Project Governance

| Role | Responsibilities | Reporting / Escalation |
| --- | --- | --- |
| Sponsor – Monisha | Clarify needs/requirements; review milestones, prototype and research direction. | Project team; material access/issues escalated via mentor. |
| Mentor – Shaun | Academic/project guidance, progress oversight and escalation support. | Course convenors where required. |
| Project team | Plan, research, design, develop, test, document and deliver; maintain tickets/minutes. | Sponsor and mentor. |
| Course convenors | Assessment governance and formal project issue resolution. | Unit governance. |

Operational decisions are recorded in meeting minutes and tickets. Material scope changes are discussed with the sponsor. Issues threatening delivery are escalated to Shaun and, where required, the course convenors.

# 9. Risk Analysis and Mitigation

| ID | Risk | Likelihood | Impact | Rating | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Institutional problem/requirements incomplete | High | High | Extreme | Document assumptions; prioritise sponsor clarification; re-baseline after confirmation. | Jordon |
| R2 | Scope exceeds semester capacity | High | High | Extreme | Protect core MVP; prioritise; defer lower-value features. | All |
| R3 | Sponsor availability delays decisions | Medium | High | High | Fortnightly meetings, written decision logs and escalation if required. | Jordon |
| R4 | Research paper expectations unclear | High | Medium | High | Confirm format, evaluation, audience and sponsor involvement early. | Noorpreet |
| R5 | Risk scoring mistaken for legal compliance | Medium | High | High | Transparent rules/limitations; no certification/legal-advice claims. | Ashvin |
| R6 | Sensitive data used in testing | Low | High | Medium | Fictional/de-identified data only; minimise fields. | All |
| R7 | Authentication/RBAC weakness | Medium | High | High | API-level authorisation, secure credentials and security review. | Avnish |
| R8 | Integration defects | Medium | High | High | Agree interfaces early; incremental integration/regression tests. | Avnish/Ashvin |
| R9 | Uneven workload | Medium | Medium | Medium | Owners/hours in tickets; weekly workload review. | All |
| R10 | Accessibility/usability insufficient | Medium | Medium | Medium | Plain-language design, accessibility criteria and workflow testing. | Jordon/Noorpreet |

# 10. Stakeholder Analysis and Communication Plan

| Stakeholder | Interest | Influence | Need / Interest |
| --- | --- | --- | --- |
| Sponsor / SREC | High | High | Useful prototype, governance workflow, future-development value and research output. |
| Faculty users | High | High | Simple workflow, clear status and minimal specialist jargon. |
| Institutional governance/compliance role (title TBC) | High | High | Institution-wide visibility, risk/action monitoring and reporting. |
| Project team | High | High | Clear scope, workload, decisions and successful delivery. |
| Mentor – Shaun | High | High | Progress, risk management and professional delivery. |
| Course convenors | Medium | High | Assessment compliance and resolution of material issues. |
| People affected by institutional AI | High | Indirect | Privacy, security, fairness, transparency and human oversight. |

## 10.1 Stakeholder Map

| Power / Interest | Stakeholders | Strategy |
| --- | --- | --- |
| High power / high interest | Sponsor; governance/compliance role; project team; mentor | Manage closely through regular review and rapid issue resolution. |
| High power / lower direct interest | Course convenors | Keep satisfied; formal escalation/update when assessment or viability is affected. |
| Lower formal power / high interest | Faculty users; people affected by AI use | Keep informed; represent needs/impacts in requirements and usability review. |
| Lower power / lower interest | Other future institutional stakeholders not yet identified | Monitor and reassess if sponsor identifies them. |

## 10.2 Communication Plan

| Channel | Participants | Frequency | Purpose | Record |
| --- | --- | --- | --- | --- |
| Sponsor meeting | Sponsor + team | Fortnightly | Requirements, progress, feedback and decisions. | Minutes/actions |
| WhatsApp | Sponsor + team | As needed | Coordination and scheduling. | Material decisions to minutes/tickets |
| Team meeting | Project team | Weekly | Progress, blockers, workload and allocation. | Minutes/tickets |
| Mentor meeting | Team + Shaun | As scheduled | Guidance, risks and escalation. | Notes/actions |
| Email | Relevant stakeholders | As needed | Formal decisions/escalation. | Email record |
| Ticket register | Project team | Continuous | Work, ownership, effort, defects and completion. | Register |
| Git/GitHub | Development team | Continuous | Source control and technical collaboration. | Repository history |

# 11. Quality Assurance and Measures of Success

| Area | Quality / Success Criterion | Evidence |
| --- | --- | --- |
| Proposal/plan | All nine assessment components addressed; problem/scope ≤1 page and literature review 1–2 pages in final layout. | Assessment checklist review. |
| Requirements | MVP requirements have IDs, priorities, basis and acceptance criteria. | Traceability review. |
| AI registry | Create/view/edit/classify sample AI records correctly. | Functional tests. |
| Assessment | Questionnaire completes end-to-end and maps to agreed framework/policy. | Mapping + functional tests. |
| Risk/status | Deterministic and explainable result for defined scenarios. | Unit/scenario tests. |
| Actions/reminders | Owner/due date/status retained; overdue/upcoming identified. | Integration tests. |
| Dashboard | Accurately reflects demo data and agreed filters/status. | Data reconciliation. |
| Reporting | PDF/CSV summary generates with agreed fields. | Export/content review. |
| Authentication/RBAC | Protected functions inaccessible to unauthorised roles. | Security/role tests. |
| Privacy | No real sensitive data required for demo. | Pre-demo data review. |
| Usability/accessibility | Non-specialist user completes core workflow; no critical accessibility blocker. | Walkthrough/checklist. |
| Software quality | No unresolved critical/high defects; regression tests pass. | Defect/test evidence. |
| Handover | README, architecture, setup and user guidance support future development. | Independent walkthrough. |
| Sponsor value | Prototype demonstrates governance-to-compliance workflow and future-development foundation. | Sponsor feedback. |
| Research paper | Addresses agreed problem, related work, method, evaluation, findings, limitations and future work. | Internal review. |

# 12. Deliverables

- Assessment-aligned project proposal and plan.

- Confirmed requirements and framework-mapping documentation.

- Working web prototype using fictional/de-identified education-sector data.

- Version-controlled source code with README, architecture and setup guidance.

- User guide for relevant roles.

- Test evidence and defect register.

- Final sponsor/academic demonstration and handover.

- Sponsor-requested research paper; final format/evaluation subject to confirmation.

# 13. Items Subject to Sponsor Confirmation

- Detailed institutional AI governance problem and pain points.

- Final user-role names and approval/review workflow.

- Institutional policies and exact framework(s) driving assessment.

- Meaning/terminology of compliance status.

- Final feature prioritisation if scope exceeds remaining capacity.

- Deployment/infrastructure expectations.

- Research-paper format, evaluation, audience and sponsor involvement.

# 14. Source References

Sri Ramakrishna Engineering College. (2026). AI governance compliance tracker: ITS capstone project proposal [Project requirements document].

University of Canberra. (2026). ICT capstone project: Assessment 2—Project proposal and plan [Assessment explainer].